## Dissertation Log
DISSERTATION LOG
Day | Week | Month | Date | Category | Description | Target | Status | Remark
1 | V | May | 2020-05-26 | Gathering Data | - Maintenance Revision (From mas Roni) | 2020-06-15 | Close
|  |  |  | Learning Python | Learning a. Python DataScience Toolbox Part 1 b. Python DataScience Toolbox Part 2 c. Introduction to Importing Data in Python | 2020-06-29 | a. Close b. Close c. Open
2 |  |  | 2020-05-27 | Gathering Data | 1. Asking data to Outstation Departments (for Outstations' Manpower and Capability - Have e-mailed the GM for Outstation Departments 2. Asking data to Capacity Planning Department - Have contacted the Manager of Capacity Planning Department | 2020-06-15 | - Open - Open
|  |  |  | Processing Data | Aircraft Profiles | 2020-06-15 | Close
3 |  |  | 2020-05-28 | Gathering Data | 1. Asking data to Outstation Department (for Outstations' Manpower and Capability - Got some answers for the data | 2020-06-15 | Open
|  |  |  | Processing Data | Maintenance Schedule Intervals | 2020-06-15 | Open
4 |  |  | 2020-05-29 | Processing Data | Maintenance Schedule Intervals | 2020-06-15 | Close
|  |  |  | Gathering Data | - SAG Data (From Farhad) - KPI Data (From Mas Doddy) - Yearly Reliability Report (from TER-1) | 2020-06-15 | - Open - Open - Open
|  |  |  | Learning Python | Completing Introduction to Importing Data in Python | 2020-06-15 | Close | Training remainings: - Introduction to git - Writing Efficient Python Code - Introduction to Relational Databases in SQL - Database Design - Introduction to PySpark - Big Data Fundamentals with PySpark - Introduction to Spark SQL in Python - Data manipulation with pandas - Merging dataframes with pandas - Introduction to data visualization with matplotlib - Introduction to data visualization with seaborn - Model Validation in Python
5 |  |  | 2020-05-30 | Methodology | Learning Dynamic Programming |  | Open
6 |  |  | 2020-05-31 | Methodology | Learning Dynamic Programming |  | Open
7 | I | June | 2020-06-01 | Methodology | Learning Dynamic Programming |  | Close
|  |  |  | Mathematical Formulation | Formulating Mathematical Programming |  | Open
8 |  |  | 2020-06-02 | Mathematical Formulation | Formulating Mathematical Programming |  | Open
9 |  |  | 2020-06-03 | Mathematical Formulation | Formulating Mathematical Programming |  | Open | Open for Correction
10 |  |  | 2020-06-04 | Business process | Learning Company's business process |  | Open
|  |  |  | Gathering Data | - KPI Data (From Mas Doddy) - Data from Outstation Department (for Outstations' Manpower and Capability) - Data from Line Service Planning Department (for Manhours Standard) |  | Close Close Close
|  |  |  | Gathering Data | - Yearly Reliability Report (From Ghufran) - Hangar Capacity and Utlization 1. Slot utilization for Garuda and Citlink every day/month per hangar per slot; 2. TAT per event in one year 3. manpower utilization to perform the scheduled maintenance for Garuda and Citilink 4. Delay: how many days per event (planned TAT vs actual TAT) 5. Material and tool utilization per event |  | Open
|  |  |  | Dissertation | Formulating The Novelty - For the first time, the long-term AMCS from A-Check to D-check maintenance is formulated and optimised - Using the 1-year planning horizon to capture the seasonality over the flight and maintenance operations instead of day or month planning horizon - Using the stochastics to measure the slot utilization |  | Open | Open for discussion
11 |  |  | 2020-06-05 | Dissertation | - Initializing data asumption |  | Open
|  |  |  | Gathering Data | Aircraft Utilization (2019 data) (from Ghufran) |  | Close
|  |  |  | Dissertation | Creating Model's flow work |  | Open

## Gantt Chart
Timetable of the work
No | Category | Activities | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September
|  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4
1 | Software Learning | Learn Python | bar: February 1 to July 4
2 | Data Gathering | Gather initial data from company (profile, background) | bar: February 2 to February 4; May 5 to June 3
3 | Supervisor Meeting | Meet with supervisor | bar: February 3 to February 4; March 4; April 1; April 3; May 1; May 3; May 5; June 2; June 4 to September 1
4 | Interim Report | Understand the nature of research | bar: February 4 to March 1
5 |  | Conduct a literature review | bar: February 4 to March 1
6 |  | Formulate research problem | bar: February 4 to March 1
7 |  | Submit interim report | bar: March 1
8 | Dissertation | Collect the core data | bar: March 5 to June 2
9 |  | Do the algorithm | bar: June 3 to August 1
10 |  | Test the result | bar: August 1 to August 3
11 |  | Validate the result | bar: August 2 to August 4
12 |  | Compile all the result | bar: August 3 to August 5
13 |  | Submit Dissertation | bar: September 1
14 | Project Poster | Compile Project Poster | bar: August 4 to September 1
15 |  | Submit Project Poster | bar: September 2
16 | Dissertation Defence | Present Dissertation | bar: September 2

## Progress Report
Progress Report (6-Jul-2020)
| 1 | Processed the raw data to ready-to-use data (progress around 90%)
| 2 | Revised the data configuration and columns
| 3 | Inputted, processed and loaded the data and parameters to the model (the process still running)
Next Week (13-Jul-2020)
| 1 | Finishing configuring data
| 2 | Finalising all raw data to ready-to-use data
| 3 | Finishing for data and parameters load to the model
| 4 | Starting to write the function of work flow process into the model
| 5 | Starting to write the MIP function (constraints) into the model

## Progress History
Progress Report (29-Jun-2020)
| 1 | Revised the whole formulation based on the operational situation
| 2 | Formulate the whole and detailed workflow, from pre-processing and initial and scheduling data
| 3 | Started working the model
a. Still trying to figure it out about what sorts of function to be used.
b. After learning some courses and familiarise with the python function for mixed integer programming, chose to select Python MIP with the modified function by Gurobi
Next week (to 6-Jul-2020)
| 1 | Finalise gathering data (still waiting for some data given by the company)
| 2 | Finalise processing the raw data to ready-to-use data (the data given were raw, so they needed to be customised using the formula)
| 3 | Started to inputting the data and parameters in the model